## pro
Dicrease Desaster project - 2018 - Colombo District
Physical and Financial Progress of the Month of 06/06/2018
Divisional Secretariate Division (a) |  |  | Name: Kaduwela
No: 9
SN | Project No. | Name of Project | G.N.Division (b) |  | Electorate Division | Sector | Type of Project |  | Total Estimate Cost (Rs.) |  | Agreement cost(Rs.) | Allocation (Rs.) | Amount of Released Allocation(Rs.) |  |  | Expenditure | Financial Progress % | Unit of Measure |  | Physical progress (c ) | [9 empty] | No of Beneficiaries | Implementing Agency | CBO/Contractor | Starting Date | End Date
|  |  | Name | No |  |  | Construction | Purchasing |  |  |  |  | Without Adm (Rs) | Admin (Rs) 0.5% | Total (Rs) |  |  | Key Performance indicator | Value of Measurement | A | B |  |  |  | C | D | E | F | G
[9 empty] | With VAT | Without VAT | [5 empty] | Total(With VAT)(Rs.) |  |  |  |  | i | ii | iii | iv
1 |  | Refurbishment of Dobawatiyaya Center Canel at Cross to Athurugiriya Road. | Pore | 489 | Kaduwela | SA | 1 |  | - | 1872294.27 | 1847048.61 | 19000000 | 1844588.54 | 27705.73 | 1872294.27 | [9 empty] | 1 |  |  |  |  | 850 |  |  | 13.07.2018
| Total | [8 empty] | 12 | 1847048.61 | 19000000 | 1844588.54 | 27705.73 | 1872294.27 | [9 empty] | 1
|  | …………………………………………… |  |  |  |  | …………………………………… |  |  |  |  | ………………………………… | [11 empty] | …………………………
[7 empty] | Checked By |  |  |  |  | Recommened by | [11 empty] | Approved By
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos
(c ) - Instructions to fill the Physical Progress
|  | Description for rating |  |  |  |  | Rates | Percentage Ranges
|  | Estimate is being / to be prepared and initial works started |  |  |  |  | A | (0 - 5)%
|  | B - i Estimates Approved & Bid Documents Prepared |  |  |  |  | B | (6 - 25)%
B - ii Quotation / Bid called
Others: Identified Institutions/ CBO's to provide Goods / Instruments
B - iii Quotation / Bid Received
Others : Obtain required list of goods,
B - iv Contract Awarded
Others : Estimated prepared
|  | Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments |  |  |  |  | C | (26 - 40)%
|  | Constructions : 60% Completed |  |  |  |  | D | (41 - 60)%
|  | Constructions : 80% Completed Other : Received goods / instruments as per the order |  |  |  |  | E | (61 - 80)%
|  | Constructions : 99% Completed Other : Completed lists of goods and beneficiaries |  |  |  |  | F | (81 - 99)%
|  | Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  |  |  | G | 100%
|  | Constructions : 99% Completed Other : Completed lists of goods and beneficiaries |  |  |  |  | F |  | (81 - 99)%
|  | Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  |  |  | G |  | 100%
E For Constructions Projects 51% - 75% completed
For Other Projects: Received goods /instruments as per the order
F - For Constructions 76% - 99% completed
For Other Projects: Completed lists of goods and beneficiaries
G For Constructions Projects 100% completed
For Other Projects: Issued goods and instruments to identified institutions / CBOs
* Projects should be categorized for following sectors
SF- Storage Facilities
RE- Rural Economy
MI - Minor Irrigation [Constructions and renovations of canals, anicuts, ponds and agro wells under the minor irrigation projects for agricultural activities]
WS - Community Based Water Supply [Community based water supply projects both rehabilitation and new construction to improve the drinking water and common bathing]
OI - Other Infrastructure Project which leads to rural livelihood development
(Any other physical infrastructure projects which could be implemented at village level to uplift the rural livelihood]
LCD - Livelihood and Capacity Development