## Sheet1
Rural Infrastructure Development Special Programme (20Mil) - 2018
Physical and Financial Progress of the Month of 07/08/2018
Divisional Secretariat Division (a) |  | Name:Kaduwela
No: 104-02-06-06-2506
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
SN | Code of MP | Project No | Project Name | G.N. Division (b) |  | Electorate Division | Sector | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries | Measurement |  | Implementin & Agency | CBO/Contractor | Starting Date | End Date | Remarks
[18 empty] | B | [8 empty] | Expenditure (work Done) (Rs.) | Vat (Rs) | Admin Cost (Rs) | Total Expenditure (Rs)
|  |  |  | Name | No |  |  | Construction | Goods&Services |  | With VAT | Without VAT | Without Adm (Rs) | Admin (0.5%) (Rs) | Total (Rs) |  | A | i | ii | iii | iv | C | D | E | F | G | [5 empty] | Key performance indicator | Value of mesurment
1 | CW | RIDP/SP/M20/KADU/2018/01 | Construct of the Drain System and culvert Hokandara Rathnarama tempal | Arangala | 494 B | Kaduwela | RA | 1 | - | 1400000 | - | 1400000 | 1386138.62 | 6930.69 | 1393069.31 | 1386138.61 | [14 empty] | 30 |  |  | DS |  | 2018.05.14 | bar: A to B E
Total | [7 empty] | 1 | - | 1400000 | - | 1400000 | 1386138.62 | 6930.69 | 1393069.31 | 1386138.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | 30
| Description for rating | [7 empty] | Rates
| Estimate is being / to be prepared and initial works started | [7 empty] | A |  |  | (0-5)% | [19 empty] | WS- Rural Water Supply
| B - i Estimates Approved & Bid Documents Prepared | [7 empty] | B | [22 empty] | EL- Rural Electricity
| B - ii Quotation / Bid called | [30 empty] | RA- Rural Access
| Others: Identified Institutions/ CBO's to provide Goods / Instruments | [30 empty] | EI - Economic Infrastructure
| B - iii Quotation / Bid Received | [30 empty] | RW- Rural Welffare
| Others : Obtain required list of goods, | [30 empty] | CD- Community Development
| B - iv Contract Awarded | [30 empty] | MI- Minor Irrigation
| Others : Estimated prepared | [30 empty] | SW- Social Welfare
SS- Social Services
| Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments | [7 empty] | C |  |  | (26 - 40 ) % | [19 empty] | CP- Community Protection
| Constructions : 60% Completed Other : Received goods / instruments as per the order | [7 empty] | D |  |  | (41 - 60 ) % | [19 empty] | LD - Livelihood Development
| Constructions : 80% Completed Other : Received goods / instruments as per the order | [7 empty] | E |  |  | (61 - 80) % | [19 empty] | RE - Rural Economy
| Constructions : 99% Completed Other : Completed lists of goods and beneficiaries | [7 empty] | F |  |  | (81 - 99 ) %
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs | [7 empty] | G |  |  | 100%