## Sheet1
Sukitha Purawara Development Programme - 2018
Physical and Financial Progress of the Month of 06/08/2018
Divisional Secretariat Division (a) |  | Name:Kaduwela
No:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
SN | Code of MP | Project No | Project Name | G.N. Division (b) |  | Electorate Division | Sector | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries | Measurement |  | Implemention & Agency | CBO/Contractor | Starting Date | End Date | Remarks
[18 empty] | B | [8 empty] | Expenditure (work Done) (Rs.) | Vat (Rs) | Admin Cost (Rs) | Total Expenditure (Rs)
|  |  |  | Name | No |  |  | Construction | Goods&Services |  | With VAT | Without VAT | Without Adm (Rs) | Admin (1.5%) (Rs) | Total (Rs) |  | A | i | ii | iii | iv | C | D | E | F | G | [5 empty] | Key performance indicator | Value of mesurment
1 | CR | SUK/KADU/2018/01 | To lay Insert stones and make the road at Morawakawattha A play ground road 2nd lane Mr. Dammika's house to Mrs. Swarna's house (100m) | Pahala Bomiriya | 472 B | Kaduwela | RA | 1 | - | 500000 | - | 500000 | [18 empty] | 30 |  |  | DS | bar: A to B i
2 | CR | SUK/KADU/2018/02 | To lay Insert stones and make the road at Morawakawattha A play ground road 3rd Mr. Wesly Guruge lane Mr. Dammika's house to MR. Swarna Richad's house (75m) | Pahala Bomiriya | 472 B | Kaduwela | RA | 1 | - | 500000 | - | 500000 | [18 empty] | 38 |  |  | DS | bar: A to B i
3 | CR | SUK/KADU/2018/04 | To lay Insert stones and make the road at Weikewattha road near the Load Buddha Start 1st lane | Pahala Bomiriya | 472 B | Kaduwela | RA | 1 | - | 500000 | - | 500000 | [18 empty] | 125 |  |  | DS | bar: A to B i
4 | CR | SUK/KADU/2018/06 | Developing of tar ramahera road 1st lane 150m and Developing of tar left side 1st by road with near the Mr. Dasun's house 25m | Raggahawattha | 474 A | Kaduwela | RA | 1 | - | 500000 | - | 500000 | [18 empty] | 53 |  |  | DS | bar: A to B i
5 | CR | SUK/KADU/2018/07 | To lay Insert stones and make the road at near the Sisi Amma's house to Mrs. Prithi Kumari's house | Raggahawattha | 474 A | Kaduwela | RA | 1 | - | 800000 | 800000 | 686666.67 | [18 empty] | 110 |  |  | DS | bar: A to B i
6 | CR | SUK/KADU/2018/09 | Construct of the Drain System and culvert Santhalokagama jaunction | Shanthalokagama | 4847 A | Kaduwela | RA | 1 | - | 500000 | [23 empty] | PRDA | bar: A
7 | CR | SUK/KADU/2018/16 | To lay Insert stones and make the road at Ananada Bodhi Mawatha at the by road No. 234/A Mrs. Hemantha Perera to No. 235/D Mr. Jagath's house | Pore | 489 | Kaduwela | RA | 1 | - | 800000 | 800000 | 680991.74 | [18 empty] | 30 |  |  | DS | bar: A to B i
8 | CR | SUK/KADU/2018/17 | To lay Insert stones and make the road at Galpottha para by road at No. 32/5 Mrs. Rohini Sujatha's house to No. 32/A/3 Mr. Jayathilaka's house | Pore | 489 | Kaduwela | RA | 1 | - | 700000 | 700000 | 595867.77 | [18 empty] | 60 |  |  | DS | bar: A to B i
9 | CR | SUK/KADU/2018/18 | To lay Insert stones and make the road at Pore Bakmigaha road at No. 105/2 Mr. Sunil Wijewattha's house | Pore | 489 | Kaduwela | RA | 1 | - | 700000 | 700000 | 595867.77 | [18 empty] | 9 |  |  | DS | bar: A to B i
10 | CR | SUK/KADU/2018/19 | To lay Insert stones and make the road at Pore Bakmigaha road at No. 109/10 house | Pore | 489 | Kaduwela | RA | 1 | - | 500000 | - | 460000 | [18 empty] | 15 |  |  | DS | bar: A to B i
11 | CR | SUK/KADU/2018/20 | To lay Insert stones and make the road at Moratuwahena by road at 1st lane No. 191 Mr. T. Almeda's house to No. 191/5 Mr. Ananda Jayalath's house | Athurugiriya | 490 | Kaduwela | RA | 1 | - | 700000 | 700000 | 595867.77 | [18 empty] | 25 |  |  | DS | bar: A to B i
12 | CR | SUK/KADU/2018/21 | To lay Insert stones and make the road at Boralugoda main roan No. 317 Mr. Yasawardena's house to No. 317/3 Mr. Premathissa house | Boralugoda | 489 A | Kaduwela | RA | 1 | - | 300000 | [23 empty] | DS |  |  |  | 2018.06.13 නාම සංශෝධනයට යොමු කර ඇත
13 | CR | SUK/KADU/2018/22 | To lay Insert stones and make the road at Thunandahena Delgahawattha near the No. 663 Mrs. Arunakanthi to the by road No. 663/C | Thunadahena | 488 B | Kaduwela | RA | 1 | - | 800000 | - | 407000 | [18 empty] | 26 |  |  | DS | bar: A to B i
14 | CR | SUK/KADU/2018/23 | To lay Insert stones and make the road at Jayanthi Road Delgahakamatha by road No. 577/25 Mr. Ranga Athugalage's house to No. 575/6 Mr. Gamini Disanayake's House | Thaldiyavala | 490 B | Kaduwela | RA | 1 | - | 600000 | [23 empty] | DS |  |  |  | 2018.06.13 නාම සංශෝධනයට යොමු කර ඇත
15 | CR | SUK/KADU/2018/24 | To lay Insert stones and make the road at No. 205/A/1 Mrs. Dayani's house to No. 205/C Mr. Chandradasa Perera's house | Pore | 489 | Kaduwela | RA | 1 | - | 600000 | 600000 | 510743.8 | [18 empty] | 32 |  |  | DS | bar: A to B i
16 | CR | SUK/KADU/2018/25 | Developing of the carpet the road starting to Samanala Mawatha (700M) | Athurugiriya | 490 | Kaduwela | RA | 1 | - | 840000 | [23 empty] | DS |  |  |  | පූර්ව විමර්ෂණ ලබා ගැනීමට යොමුකර ඇත | bar: A
Total | [7 empty] | 16 | - | 9840000 | 4300000 | 6533005.52 | 0 | 0 | 0 | 0 | A: 2; B i: 12 | 0 |  |  |  | 553 | [6 empty] | 2
| Description for rating | [7 empty] | Rates
| Estimate is being / to be prepared and initial works started | [7 empty] | A |  |  | (0-5)% | [19 empty] | WS- Rural Water Supply
| B - i Estimates Approved & Bid Documents Prepared | [7 empty] | B |  |  | (6 -25 )% | [19 empty] | EL- Rural Electricity
| B - ii Quotation / Bid called | [30 empty] | RA- Rural Access
| Others: Identified Institutions/ CBO's to provide Goods / Instruments | [30 empty] | EI - Economic Infrastructure
| B - iii Quotation / Bid Received | [30 empty] | RW- Rural Welffare
| Others : Obtain required list of goods, | [30 empty] | CD- Community Development
| B - iv Contract Awarded | [30 empty] | MI- Minor Irrigation
| Others : Estimated prepared | [30 empty] | SW- Social Welfare
SS- Social Services
| Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments | [7 empty] | C |  |  | (26 - 40 ) % | [19 empty] | CP- Community Protection
| Constructions : 60% Completed Other : Received goods / instruments as per the order | [7 empty] | D |  |  | (41 - 60 ) % | [19 empty] | LD - Livelihood Development
| Constructions : 80% Completed Other : Received goods / instruments as per the order | [7 empty] | E |  |  | (61 - 80) % | [19 empty] | RE - Rural Economy
| Constructions : 99% Completed Other : Completed lists of goods and beneficiaries | [7 empty] | F |  |  | (81 - 99 ) %
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs | [7 empty] | G |  |  | 100%